## Sheet1
Findings Register : NexaCore
FindingID | Title | ControlArea | Condition | Criteria | RootCause | Risk | Impact | Recommendation | Owner | Priority | Status | ManagementResponse
FND-01 | Excessive privilege on Finance Platform | IAM-07/IAM-13 | J. Alvarez holds admin access with no approval record | Access should match approved role | Likely temporary grant never reverted | Excess privilege increases impact of error or compromise | Medium | Right-size to Analyst role or document justification | L. Bianchi | High | Open | Agree - remediation planned
FND-02 | Unapproved MFA exception with SoD pattern | IAM-14/IAM-17 | N. Okafor has an undocumented MFA exception and a related SoD conflict | MFA exceptions must be approved; SoD conflicts need compensating controls | Exception granted informally and never re-reviewed | Weakens authentication control and payroll SoD integrity | Medium | Formalize or revoke exception; re-confirm compensating control | HR Director | Medium | Open | Partially agree
FND-03 | MFA not enforced for standard users | IAM-17 | T. Whitfield and M. Fischer active without MFA or exception | MFA required for all active accounts | Inconsistent enrollment enforcement at onboarding | Increases credential-compromise risk | Medium | Enforce MFA immediately for both accounts | IT/IAM Administrator | High | Open | Agree
FND-04 | Undocumented privileged access grant | IAM-07/IAM-15 | D. Kapoor's Cloud Administrator access has no approval record | Privileged access requires documented approval | Recurring gap in privileged onboarding process | High-impact access without accountability trail | High | Obtain retroactive approval or revoke; fix onboarding checklist | CISO | High | Open | Agree - remediation planned
FND-05 | Privileged account missing MFA and review | IAM-15/IAM-17 | V. Andersen has no MFA and no review on record | Enhanced MFA and periodic review required for privileged accounts | Onboarding checklist gap | Highest-impact scenario in population - security tooling itself at risk | High | Enforce MFA immediately; complete overdue review | CISO | Critical | Open | Agree - urgent remediation
FND-06 | Service account review overdue | IAM-16 | svc-salesforce-sync last reviewed 2025-11-20 exceeding cadence | Semi-annual review required | Review process did not flag overdue service accounts | Unreviewed elevated-adjacent access | Low-Medium | Complete review; add to review-tracking process | P. Reyes | Medium | Open | Agree
FND-07 | Contractor access without expiration | IAM-10/IAM-17 | K. Novotny's access has no end date and no MFA | Contractor access must be time-bound and MFA-enforced | Access request template lacked mandatory end-date field | Standing access risk beyond engagement scope | Medium | Add expiration date; enforce MFA | S. Novak | Medium | Open | Agree - remediation planned
FND-08 | Orphaned privileged service account | IAM-16 | svc-ci-deploy has no owner and unknown approval status | Service accounts require named owner | Owner departed without handover | Unaccountable privileged access to production repos | High | Assign owner; obtain approval record; consider decommissioning if unused | IT/IAM Administrator | High | Open | Agree - remediation planned
FND-09 | Terminated contractor retains access | IAM-09/IAM-10 | E. Marsh's Salesforce access active 10 days past contract end | Access removed at contract end | Deprovisioning not triggered on contract-end date | Unauthorized access by a non-engaged party | Medium | Remove access immediately | IT/IAM Administrator | High | Open | Agree - immediate action
FND-10 | Mover access not removed | IAM-08 | H. Lindqvist retains old Finance Platform access after transfer to Sales | Role change should trigger access review and removal | Mover checklist step skipped | Excess access outside current role | Medium | Remove old Finance access | IT/IAM Administrator | Medium | Open | Agree