## Sheet1
IAM Risk Register
RiskID | FindingID | RiskStatement | AssetSystem | Threat | Vulnerability | Likelihood | Impact | InherentRisk | ExistingControls | ResidualRisk | RiskOwner | Treatment | Status
RSK-01 | FND-01 | Excessive Finance Platform privilege could enable unauthorized financial changes | Finance Platform | Insider error or account compromise | Unapproved admin access | Medium | Medium | Medium | None specific | Medium | L. Bianchi | Mitigate - right-size access | Open
RSK-02 | FND-02 | Unreviewed HR/Payroll SoD conflict could allow unauthorized payroll change | HRIS / Finance Platform | Fraud or error | Combined create+approve capability | Low | Medium | Medium | Monthly payroll reconciliation | Low | N. Okafor's manager | Monitor - compensating control adequate | Open
RSK-03 | FND-03 | Missing MFA increases credential compromise likelihood for standard users | Salesforce / M365 | Credential theft/phishing | No second authentication factor | Medium | Medium | Medium | None | Medium | IT/IAM Administrator | Mitigate - enforce MFA | Open
RSK-04 | FND-04 | Undocumented privileged access grant lacks accountability if misused | Cloud Environment | Insider misuse or compromise | No approval trail for privileged grant | Medium | High | High | None | High | CISO | Mitigate - retroactive approval + process fix | Open
RSK-05 | FND-05 | Privileged security-admin account without MFA is a high-impact compromise vector | Cloud Env / M365 Security | Credential compromise of security tooling | No MFA, no review | Medium | High | High | None | High | CISO | Mitigate - urgent MFA enforcement | Open
RSK-06 | FND-06 | Overdue service account review could miss unauthorized changes | Salesforce / HRIS | Undetected permission drift | Review cadence not honored | Low | Low | Low | Vaulted credentials | Low | P. Reyes | Monitor - complete review | Open
RSK-07 | FND-07 | Contractor access without expiration risks standing unauthorized access | Cloud Environment | Access outlives business need | No expiration control | Medium | Medium | Medium | None | Medium | S. Novak | Mitigate - add expiration + MFA | Open
RSK-08 | FND-08 | Orphaned privileged service account has no accountable party if compromised | GitHub / Cloud Env | Unmonitored privileged misuse | No owner, unclear approval | Medium | High | High | None | High | IT/IAM Administrator | Mitigate - assign owner or decommission | Open
RSK-09 | FND-09 | Terminated contractor's active access enables unauthorized data access | Salesforce | Unauthorized access by former contractor | Deprovisioning not triggered | Medium | Medium | Medium | None | Medium | IT/IAM Administrator | Mitigate - remove access immediately | Open
RSK-10 | FND-10 | Retained mover access creates excess exposure outside current role | Finance Platform | Excess access misuse | Mover checklist step skipped | Low | Medium | Low-Medium | None | Low-Medium | IT/IAM Administrator | Mitigate - remove old access | Open